## Sprint Plan
SpaceLandMapper – Sprint Plan
Project: AI Land Classification using Sentinel-2 Satellite Imagery ¦ Methodology: Agile/Scrum
Sprint Range | Dates | Phase | Sprint Goal | Key Deliverables | Team Responsibility
Sprint 1–4 | 14 Oct – 10 Nov 2025 | Discovery & Planning | Define problem, roles, project scope | Problem statement, roles, PID draft | All (Led by Abdullah)
Sprint 5–7 | 11 Nov – 1 Dec 2025 | Research & System Design | Research, dataset understanding, pipeline design | Literature review, dataset analysis, pipeline diagram | Mishal (Lead), Hamza supports
Sprint 8–10 | 2 Dec 2025 – 5 Jan 2026 | Research Report & Prep | Complete Element 1 and prepare for development | Research report, documentation | Mishal (Lead), Altamash supports
Sprint 11–12 | 6 Jan – 19 Jan 2026 | Setup & Data Preparation | Setup environment and prepare dataset | GitHub repo, dataset splits | Hamza (Lead), Abdullah supports
Sprint 13–15 | 20 Jan – 9 Feb 2026 | Baseline Development | Build and evaluate baseline model | Baseline model, metrics, confusion matrix | Abdullah (Lead), Altamash evaluates
Sprint 16–18 | 10 Feb – 2 Mar 2026 | CNN Development | Design, train, and evaluate CNN | CNN model, improved performance | Abdullah (Lead), Altamash evaluates
Sprint 19–20 | 3 Mar – 16 Mar 2026 | Output & Repo Finalisation | Save outputs and organise repository | Model outputs, cleaned repo | All (Altamash prepares dashboard)
Sprint 21–23 | 17 Mar – 30 Mar 2026 | Dashboard Development | Build dashboard and integrate model | Streamlit dashboard with prediction | Altamash (Lead), Abdullah supports
Sprint 24–25 | 31 Mar – 7 Apr 2026 | UI & System Refinement | Improve UI, testing, polishing | Final dashboard, improved UI | Altamash (Lead), Mishal documents
Sprint 26–29 | 8 Apr – 17 Apr 2026 | Finalisation & Submission | Prepare demo, slides, and submission | Presentation, demo, README, final repo | All (Abdullah leads presentation)