## Gantt Chart
SpaceLandMapper — Project Gantt Chart
Task / Deliverable | Assigned To | Start | End | Status | 13 Oct | 20 Oct | 27 Oct | 03 Nov | 10 Nov | 17 Nov | 24 Nov | 01 Dec | 08 Dec | 15 Dec | 22 Dec | 29 Dec | 05 Jan | 12 Jan | 19 Jan | 26 Jan | 02 Feb | 09 Feb | 16 Feb | 23 Feb | 02 Mar | 09 Mar | 16 Mar | 23 Mar | 30 Mar | 06 Apr | 13 Apr
Sprint 1 — Discovery & Planning
Define problem statement and project scope | Abdullah Hassan | 2025-10-14 | 2025-10-24 | Done | ■ | ■
Assign team roles and establish collaboration workflow | Abdullah Hassan | 2025-10-14 | 2025-10-27 | Done | ■ | ■ | ■
Draft PID and initial project documentation | Mishal Zahra | 2025-10-21 | 2025-11-10 | Done |  | ■ | ■ | ■ | ■
Sprint 2 — Research & System Design
Research Sentinel-2 context and Earth Observation use cases | Mishal Zahra | 2025-11-11 | 2025-11-20 | Done |  |  |  |  | ■ | ■
Explore EuroSAT classes and assess data quality | Hamza Kounan | 2025-11-11 | 2025-11-24 | Done |  |  |  |  | ■ | ■ | ■
Design initial pipeline and model comparison approach | Abdullah Hassan | 2025-11-18 | 2025-12-01 | Done | [5 empty] | ■ | ■ | ■
Sprint 3 — Research Report & Preparation
Complete research report and literature synthesis | Mishal Zahra | 2025-12-02 | 2025-12-22 | Done | [7 empty] | ■ | ■ | ■ | ■
Prepare reproducibility notes and documentation structure | Mishal Zahra | 2025-12-09 | 2025-12-29 | Done | [8 empty] | ■ | ■ | ■ | ■
Review findings and plan transition into development | All Team | 2025-12-23 | 2026-01-05 | Done | [10 empty] | ■ | ■ | ■
Sprint 4 — Setup & Data Preparation
Set up environment and confirm repository structure | Abdullah Hassan | 2026-01-06 | 2026-01-12 | Done | [12 empty] | ■ | ■
Define preprocessing steps for consistent training | Hamza Kounan | 2026-01-06 | 2026-01-16 | Done | [12 empty] | ■ | ■
Create reproducible train / validation / test split | Hamza Kounan | 2026-01-10 | 2026-01-19 | Done | [12 empty] | ■ | ■ | ■
Sprint 5 — Baseline Development
Build baseline model as initial benchmark | Abdullah Hassan | 2026-01-20 | 2026-01-31 | Done | [14 empty] | ■ | ■
Generate baseline metrics and confusion matrix | Altamash Khan | 2026-01-27 | 2026-02-05 | Done | [15 empty] | ■ | ■
Review baseline results and error patterns | Abdullah Hassan / Altamash Khan | 2026-02-01 | 2026-02-09 | Done | [15 empty] | ■ | ■ | ■
Sprint 6 — CNN Development
Build and train CNN model | Abdullah Hassan | 2026-02-10 | 2026-02-21 | Done | [17 empty] | ■ | ■
Evaluate CNN with metrics and confusion matrix | Altamash Khan | 2026-02-17 | 2026-02-27 | Done | [18 empty] | ■ | ■
Compare baseline and CNN to select final model | Abdullah Hassan / Altamash Khan | 2026-02-24 | 2026-03-02 | Done | [19 empty] | ■ | ■
Sprint 7 — Dashboard, Finalisation & Submission
Organise outputs, README and repository finalisation | Mishal Zahra / Abdullah Hassan | 2026-03-03 | 2026-03-16 | Done | [20 empty] | ■ | ■ | ■
Build and refine Streamlit dashboard | Altamash Khan | 2026-03-17 | 2026-04-07 | Done | [22 empty] | ■ | ■ | ■ | ■
Final testing, demo preparation and submission pack | All Team | 2026-04-08 | 2026-04-17 | Done | [25 empty] | ■ | ■