## PRODUCT BACKLOG
🛰 SpaceLandMapper – Product Backlog (Updated)
Project: AI Land Classification using Sentinel-2 Satellite Imagery ¦ Methodology: Agile/Scrum
Priority: 🔴 Must Have 🟠 Should Have 🟡 Could Have ⚪ Won't Have (MoSCoW) Status: Planned ¦ In Progress ¦ Done
ID | User Story | Epic / Theme | Story Points | Owner (Test Plan Aligned) | Linked Test Cases | Acceptance Criteria (Done when…) | Status | Priority | Contingency / Backlog Plan | Risk Level
PB-01 | As a team, we want the dataset confirmed and accessible so we can start building the pipeline | Data Acquisition | 3 | Mishal Zahra | TC1, TC10 | EuroSAT dataset source agreed; access method documented; class list confirmed (10 classes) | Completed | 🔴 Must Have | Delay in dataset confirmation risks entire sprint 1. Contingency: Use EuroSAT sample subset immediately; full dataset access to be resolved within 3 days or escalate to supervisor Dr. Panesar. | Low
PB-02 | As a modeller, we want a clear label mapping so classes are consistent across the whole pipeline | Data Acquisition | 2 | Mishal Zahra | TC1 | Label map saved (class → ID); used in training and dashboard; version-controlled | Completed | 🔴 Must Have | Inconsistent labels will cascade errors through training. Contingency: Adopt EuroSAT's default class mapping as interim standard; Mishal to deliver final mapping within 2 days of dataset access. | Low
PB-03 | As a team, we want preprocessing steps defined so training and inference are consistent | Data Processing | 5 | Hamza Kounane | TC2, TC3 | Preprocess v1 defined (resize 64×64 + normalise 0–1); steps fully documented | Completed | 🔴 Must Have | Missing preprocessing definition blocks PB-04 and all model items. Contingency: Hamza to deliver at least resize+normalise spec by end of sprint 1; advanced steps (augmentation) move to sprint 2. | Medium
PB-04 | As a team, we want a reproducible train/val/test split so evaluation is fair | Data Processing | 3 | Hamza Kounane | TC4 | Stratified 70/15/15 split created; seed recorded; class distribution checked | Completed | 🔴 Must Have | Unfair splits may invalidate evaluation. Contingency: If stratification tool fails, use manual split per class; document seed and distribution; Abdullah to cross-verify ratios before model training begins. | Medium
PB-05 | As a team, we want a baseline model so we have a benchmark result to compare against | Model Development | 5 | Abdullah Hassan | TC5 | Baseline (Random Forest/KNN) runs end-to-end; predictions saved; metrics produced | Completed | 🔴 Must Have | Baseline failure blocks comparison in PB-07/08/09/12. Contingency: Simplify to a single KNN with default params; Abdullah to deliver at least predictions CSV even if metrics are basic. | Medium
PB-06 | As a team, we want a CNN model (v1) to compare against the baseline | Model Development | 8 | Abdullah Hassan | TC6 | CNN trains; model saved (.h5/.pt); predictions saved; accuracy + macro-F1 produced | Completed | 🔴 Must Have | CNN failure is the highest-risk item. Contingency: Reduce to a 3-layer CNN; cut hyperparameter search; accept lower accuracy; if GPU unavailable, switch to CPU-friendly MobileNet v2 pretrained. | High
PB-07 | As a reviewer, we want standard metrics so model performance is easy to compare | Evaluation | 3 | Abdullah Hassan & Altamash Khan | TC7, TC8, TC9 | Accuracy + macro-F1 + confusion matrix generated and saved in results folder | Completed | 🔴 Must Have | Missing metrics make evaluation report impossible. Contingency: At minimum produce accuracy and confusion matrix from saved predictions; macro-F1 added in sprint 4 if delayed. | Medium
PB-08 | As a team, we want an experiment log so each run is reproducible | Evaluation | 2 | Mishal Zahra | TC1, TC5 | Log records run ID, seed, key hyperparameters, and metrics for every run | Completed | 🟠 Should Have | No experiment log makes results unreproducible. Contingency: Use a plain CSV log as fallback; Mishal to maintain manually if automated logging fails. | Low
PB-09 | As a user, we want sample predictions saved so results are easy to show in demos | Evaluation | 3 | Altamash Khan | TC14, TC15 | ≥20 example predictions saved (correct + incorrect) with ground-truth labels | Completed | 🟠 Should Have | No sample predictions weakens dashboard demo. Contingency: Altamash to collect minimum 10 correct + 5 incorrect examples; screenshots accepted if file export breaks. | Low
PB-10 | As a user, we want a Streamlit dashboard so I can view results in one place | Dashboard | 8 | Altamash Khan & Abdullah Hassan | TC12, TC13, TC16 | Dashboard runs locally; shows accuracy, macro-F1, confusion matrix, sample predictions | Completed | 🔴 Must Have | Dashboard failure is critical for demo. Contingency: Altamash to have a static HTML fallback with exported figures if Streamlit fails; basic display of accuracy + confusion matrix is minimum. | High
PB-11 | As a user, we want a model selector so I can switch between baseline and CNN outputs | Dashboard | 3 | Altamash Khan | TC13, TC14, TC15 | Toggle/dropdown works; dashboard updates all outputs correctly when switched | Completed | 🟠 Should Have | Model selector failure degrades UX but is non-critical. Contingency: Show results for each model separately on two tabs; toggle can be deferred to final sprint if needed. | Medium
PB-12 | As a team, we want a short error analysis so we can explain model mistakes | Evaluation | 3 | Abdullah Hassan & Altamash Khan | TC7, TC8, TC9 | Top 5 confusions identified; 5–10 errors explained with examples in report | Completed | 🟠 Should Have | Error analysis may be cut if time is short. Contingency: Minimum 3 confusions identified; qualitative explanation acceptable if quantitative analysis is incomplete. | Low
PB-13 | As a team, we want a 'how to run' guide so the marker can reproduce the demo | Documentation | 3 | Hamza Kounane | TC17 | Steps documented: environment setup → training (optional) → launch dashboard | Completed | 🔴 Must Have | Missing run guide fails marking criteria. Contingency: Mishal to draft a 1-page README by sprint 5 regardless of project state; always deliverable even if dashboard is incomplete. | Low
PB-14 | As a team, we want regular blog updates as evidence of agile progress | Documentation | 2 | All Members | TC18, TC19 | Weekly blog entries done (what we did / what we learned / what's next + evidence) | Completed | 🔴 Must Have | Missing blog entries are an assessed artefact. Contingency: All members to contribute at least one paragraph per week; retrospective catch-up entries are acceptable up to 2 weeks late. | Low
PB-15 | As a team, we want final packaging so submission is complete and reproducible | Submission | 5 | Abdullah Hassan | TC18, TC19 | Final files organised; dashboard works; outputs included; instructions ready; zipped | Completed | 🔴 Must Have | Incomplete packaging fails submission. Contingency: Abdullah to create a checklist (model, dashboard, data, README, report); incomplete items to be flagged to supervisor 1 week before deadline. | High
TOTAL |  |  | 58