## Risk Register
SpaceLandMapper Risk Assessment Register
Project |  | Team Lead |  | Review Date |  | Overall Risk |  |  | Scoring Guide
SpaceLandMapper |  | Abdullah Hassan |  | 16-Apr-2026 |  | Medium |  |  | Likelihood | 1 = Low, 2 = Medium, 3 = High
[9 empty] | Impact | 1 = Low, 2 = Medium, 3 = High
[9 empty] | Priority | 1–2 Low ¦ 3–4 Medium ¦ 6–9 High
Risk ID | Category | Risk Description | Cause / Trigger | Likelihood | Impact | Score | Priority | Mitigation / Control | Contingency Action | Owner | Status | Review Notes
R1 | Technical | Streamlit dashboard fails to open during presentation | Missing packages, broken environment, or local path issues | 2 | 3 | 6 | High | Test the app in the same virtual environment before presentation and keep setup instructions in README | Use backup screenshots or video if the live app fails | Abdullah Hassan | Closed | Recent setup issue was fixed by activating .venv and using python -m streamlit
R2 | Technical | Model file or outputs cannot be loaded by the dashboard | Incorrect file path, missing outputs, or renamed folders | 2 | 3 | 6 | High | Keep outputs in the expected folders and test all dashboard tabs before submission | Re-run the CNN script if required and keep a backup copy of outputs | Abdullah Hassan | Closed | Model and outputs already exist in the outputs folder
R3 | Data | Dataset issues reduce model reliability or consistency | Insufficient checking during preprocessing or split creation | 1 | 2 | 2 | Low | Use fixed train/validation/test split and review class mapping carefully | Document dataset limitations clearly in slides and report | Hamza Kounan | Closed | EuroSAT benchmark kept scope controlled
R4 | Evaluation | Metrics are misreported across slides, README, and docs | Manual copying of scores into multiple documents | 2 | 2 | 4 | Medium | Use saved metrics.json and the final confirmed figures everywhere | Cross-check slides, README, and report before final submission | Altamash Khan | Closed | Accuracy and Macro F1 were already confirmed
R5 | Project Management | Sprint and backlog documents become inconsistent | Different versions edited separately near the deadline | 2 | 2 | 4 | Medium | Keep PM documents aligned to one product backlog and one sprint plan | Perform a final consistency review before submission | Mishal Zahra | Closed | PM files were recently aligned
R6 | Documentation | README or reproducibility steps are unclear for tutors | Commands differ from the actual working environment | 2 | 2 | 4 | Medium | Show virtual environment activation and exact dashboard launch command in README | Clarify setup verbally during demo if needed | Abdullah Hassan | Closed | README was updated after the Streamlit setup issue
R7 | Presentation | Presentation and demo repeat the same content | Poor separation between explanation and proof of functionality | 2 | 2 | 4 | Medium | Use slides to explain the journey and demo to show the app working | Keep a short demo script and role-based speaking order | Abdullah Hassan | Closed | Teacher explicitly asked for separation
R8 | Timing | Group exceeds 20-minute presentation limit | Too much detail in slides or a long demo | 2 | 3 | 6 | High | Keep the live demo short and rehearse as a group | Cut lower-priority explanation if timing becomes tight | Altamash Khan | Open | Presentation still needs full rehearsal
R9 | Submission | Canvas zip or GitHub repo is missing a required file | Last-minute packaging or linking mistakes | 2 | 3 | 6 | High | Check repo links, README, slides, PM docs, and final zip against the checklist | Upload revised zip before the deadline if something is missing | Mishal Zahra | Closed | Submission pack should be checked early
R10 | Ethics / Scope | Project overclaims full real-time land-use change monitoring | Mismatch between brief wording and current prototype scope | 2 | 2 | 4 | Medium | State clearly that the prototype focuses on land classification and treats change monitoring as future work | Clarify scope during Q&A if challenged | ALL | Open | Important wording point for presentation and docs

## Top Risks
Top Risks Dashboard
Priority | Count
High | 4
Medium | 5
Low | 1
Risk ID | Top Risk | Owner | Immediate Action | Status | Priority
R1 | Dashboard fails during presentation | Abdullah Hassan | Test app in .venv and keep backup screenshots | Open | High
R8 | Presentation exceeds time limit | Abdullah Hassan | Rehearse full run and shorten demo | Open | High
R9 | Missing file in final submission | Mishal Zahra | Run final checklist before upload | Open | High