## Sprint Backlog
SpaceLandMapper — Sprint Backlog
PB ID | User Story | Epic / Theme | Assigned To | Priority | Story Pts | Sprint | Start | End | Status
Sprint 1 — Discovery & Planning (14 Oct 2025 – 10 Nov 2025)
PB-01 | As a team, we want the dataset confirmed and accessible so we can start building the pipeline | Data Acquisition | Mishal Zahra | 🔴 Must Have | 3 | Sprint 1 | 2025-10-14 | 2025-11-10 | Done
PB-02 | As a modeller, we want a clear label mapping so classes are consistent across the whole pipeline | Data Acquisition | Mishal Zahra | 🔴 Must Have | 2 | Sprint 1 | 2025-10-14 | 2025-11-10 | Done
PB-14 | As a team, we want regular blog updates as evidence of agile progress | Documentation | All Members | 🔴 Must Have | 2 | Sprint 1 | 2025-10-14 | 2025-11-10 | Done
Sprint 2 — Research & System Design (11 Nov 2025 – 1 Dec 2025)
PB-03 | As a team, we want preprocessing steps defined so training and inference are consistent | Data Processing | Hamza Kounane | 🔴 Must Have | 5 | Sprint 2 | 2025-11-11 | 2025-12-01 | Done
PB-04 | As a team, we want a reproducible train/val/test split so evaluation is fair | Data Processing | Hamza Kounane | 🔴 Must Have | 3 | Sprint 2 | 2025-11-11 | 2025-12-01 | Done
Sprint 3 — Research Report & Preparation (2 Dec 2025 – 5 Jan 2026)
PB-05 | As a team, we want a baseline model so we have a benchmark result to compare against | Model Development | Abdullah Hassan | 🔴 Must Have | 5 | Sprint 3 | 2025-12-02 | 2026-01-05 | Done
PB-08 | As a team, we want an experiment log so each run is reproducible | Evaluation | Mishal Zahra | 🟠 Should Have | 2 | Sprint 3 | 2025-12-02 | 2026-01-05 | Done
Sprint 4 — Setup & Data Preparation (6 Jan 2026 – 19 Jan 2026)
PB-06 | As a team, we want a CNN model (v1) to compare against the baseline | Model Development | Abdullah Hassan | 🔴 Must Have | 8 | Sprint 4 | 2026-01-06 | 2026-01-19 | Done
PB-07 | As a reviewer, we want standard metrics so model performance is easy to compare | Evaluation | Abdullah Hassan & Altamash Khan | 🔴 Must Have | 3 | Sprint 4 | 2026-01-06 | 2026-01-19 | Done
Sprint 5 — Baseline Development (20 Jan 2026 – 9 Feb 2026)
PB-09 | As a user, we want sample predictions saved so results are easy to show in demos | Evaluation | Altamash Khan | 🟠 Should Have | 3 | Sprint 5 | 2026-01-20 | 2026-02-09 | Done
PB-10 | As a user, we want a Streamlit dashboard so I can view results in one place | Dashboard | Altamash Khan & Abdullah Hassan | 🔴 Must Have | 8 | Sprint 5 | 2026-01-20 | 2026-02-09 | Done
Sprint 6 — CNN Development (10 Feb 2026 – 2 Mar 2026)
PB-11 | As a user, we want a model selector so I can switch between baseline and CNN outputs | Dashboard | Altamash Khan | 🟠 Should Have | 3 | Sprint 6 | 2026-02-10 | 2026-03-02 | Done
PB-12 | As a team, we want a short error analysis so we can explain model mistakes | Evaluation | Abdullah Hassan & Altamash Khan | 🟠 Should Have | 3 | Sprint 6 | 2026-02-10 | 2026-03-02 | Done
PB-13 | As a team, we want a 'how to run' guide so the marker can reproduce the demo | Documentation | Hamza Kounane | 🔴 Must Have | 3 | Sprint 6 | 2026-02-10 | 2026-03-02 | Done
Sprint 7 — Dashboard, Finalisation & Submission (3 Mar 2026 – 17 Apr 2026)
PB-15 | As a team, we want final packaging so submission is complete and reproducible | Submission | Abdullah Hassan | 🔴 Must Have | 5 | Sprint 7 | 2026-03-03 | 2026-04-17 | Done