## COMMUNICATION PLAN
📡 SpaceLandMapper – Communication Plan
Project: AI Land Classification ¦ Period: Oct 2025 – Apr 2026 ¦ Team: Abdullah Hassan, Hamza Kounane, Altamash Khan, Mishal
Project Name: | SpaceLandMapper – AI Land Classification
Supervisor: | Dr. Kulvinder Panesar
Prepared by: | Abdullah Hassan (Team Lead)
Date: | April 2026
SECTION A – STAKEHOLDER REGISTER
# | Stakeholder | Role | Interest / Concern | Influence | Comm. Preference | Contact | Notes
1 | Abdullah Hassan | Team Lead / Lead ML Engineer | Delivery of model, project success | High | MS Teams, GitHub, Email | Ahassa23@bradford.ac.uk | Responsible for sprints & code review
2 | Hamza Kounane | Data Preprocessing Specialist | Data quality, preprocessing correctness | High | MS Teams, GitHub | Hkounane@bradford.ac.uk | Owns EuroSAT pipeline & data docs
3 | Altamash Khan | Dashboard organiser | Dashboard usability | High | MS Teams, GitHub | Akhan368@bradford.ac.uk | Owns Streamlit app & evaluation scripts
4 | Mishal | Evaluation Lead | metrics accuracy | High | MS Teams, GitHub | mzahra@bradford.ac.uk | Owns Streamlit app & evaluation scripts
5 | Dr. Kulvinder Panesar | Academic Supervisor | Academic quality, technical rigour | High | Email, Formal Reports | K.Panesar@bradford.ac.uk | Weekly check-in; feedback on milestones
SECTION B – COMMUNICATION MATRIX
# | Communication Event | Audience | Frequency | Channel / Medium | Owner | Format | Purpose
C-01 | Daily Stand-up (Async) | Full Team | Daily (weekdays) | MS Teams – text post | Team Lead | Bullet: Done / Doing / Blocked | Track progress; surface blockers early
C-02 | Sprint Planning Meeting | Full Team | Every Monday (start of sprint) | MS Teams video call | Team Lead | Agenda + Sprint Backlog update | Agree sprint goal & task assignments
C-03 | Sprint Review / Demo | Full Team + Supervisor (optional) | Every Friday (end of sprint) | MS Teams video call | Team Lead | Live demo + retrospective notes | Inspect increment; gather feedback
C-04 | Sprint Retrospective | Full Team | Every Friday (post-review) | MS Teams / shared doc | Team Lead | Keep / Stop / Start template | Continuous process improvement
C-05 | Supervisor Check-in | Team + Dr. Panesar | Weekly | Email / scheduled meeting | Abdullah Hassan | Progress update email or meeting notes | Academic guidance; milestone sign-off
C-06 | Client Progress Update | Team + Voung Mai | Bi-weekly (every 2 sprints) | Email + brief report | Abdullah Hassan | 1-page summary + dashboard screenshot | Keep client informed; validate direction
C-07 | Milestone Delivery Notification | Team + Supervisor + Client | At each milestone | Email | Abdullah Hassan | Formal milestone email with artefacts attached | Confirm delivery; obtain sign-off
C-08 | Risk / Issue Escalation | Relevant stakeholders | As needed (within 24 hrs) | Email + MS Teams alert | Team Lead | Risk log entry + escalation note | Resolve blockers; manage expectations
C-09 | Blog / Progress Log Update | Public / Supervisor | Weekly | Project blog / shared drive | All Members | Short narrative + evidence (screenshots) | Demonstrate agile working; assessment evidence
C-10 | Final Presentation & Demo | Full Team + Supervisor + Client | Once (3 Apr 2026) | In-person / MS Teams | Abdullah Hassan | Slide deck + live Streamlit demo | Deliver final product; assessment submission
SECTION C – ESCALATION PATH
Issue Level | Description | First Point of Contact | Escalation To | Timeline | Resolution Method
Level 1 – Low | Task delay (< 2 days) | Responsible team member | Team Lead (Abdullah) | Same day | Reassign task; adjust sprint plan
Level 2 – Medium | Blocker affecting sprint goal; technical issue | Team Lead | Full team + Supervisor (Dr. Panesar) via email | Within 24 hrs | Emergency team meeting; scope adjustment
Level 3 – High | Member absence; critical data/compute failure | Team Lead | Supervisor formally notified; client if delivery impacted | Within 24 hrs | Formal reassignment; scope negotiation with supervisor
Level 4 – Critical | Major scope change; ethical issue | Team Lead + Supervisor | University channels; formal documentation | Immediately | Follow university escalation procedures