Project Charter

SpaceLandMapper

1. Executive Summary

SpaceLandMapper is an artificial intelligence project, which is a team-oriented undertaking aiming to build a working prototype of a machine-learning-based image-based prediction and an interactive dashboard. The project will include research, data selection, preprocessing, model building, evaluation, GitHub documentation, integrating the dashboard, and final testing. The project will be going between 14 October 2025 and 17 April 2026, and the final live presentation will be on 20 April 2026.

2. Project Goal

This project aims to create, construct, test, and demonstrate a working prototype of AI by 17 April 2026. The chosen and ready dataset, a baseline model, a CNN model, evaluation metrics, a GitHub repository with documentation, and a Streamlit dashboard enabling users to upload pictures and get the results of prediction should be incorporated into the final solution.

3. Business Case / Background

This is a project that is being undertaken in the Discipline-specific Artificial Intelligence Project module. The idea is to implement AI methods to a real-world issue by a full development cycle, such as planning, researching, implementing, testing, and presenting. The project will assist the team in applying practical skills in the development of AI, project collaboration, technical reporting, and software delivery. It is also in line with the assignment criteria of developing a functional AI prototype with documentation, assessment, and a live demonstration.

4. Project Team and Roles

The project team consists of four members, each contributing to specific parts of the solution:

- Abdullah Hassan — Team Leader / Lead Data and Model Engineer

- Altamash Khan — Dashboard and Evaluation Lead

- Mishal Zahra — Research, Documentation and Reproducibility Lead

- Hamza Kounan — Data Preprocessing and Quality Specialist

5. Key Deliverables:

The main project deliverables, based on the sprint plan and project progress, are:

- problem statement and project planning material

- literature research and dataset selection

- preprocessed dataset

- configured development environment in VS Code

- GitHub repository

- README documentation

- baseline model

- CNN model

- evaluation metrics and accuracy results

- Streamlit dashboard

- dashboard-based image testing results

- final presentation and live demo materials

6. Project Timeline:

The project follows the sprint schedule already defined in the planning documents:

- Sprint 1–4 (14 Oct – 10 Nov 2025): Discovery and planning

- Sprint 5–7 (11 Nov – 1 Dec 2025): Research and dataset understanding

- Sprint 8–10 (2 Dec 2025 – 5 Jan 2026): Research report and supporting documentation

- Sprint 11–12 (6 Jan – 19 Jan 2026): Environment setup and dataset preprocessing

- Sprint 13–15 (20 Jan – 9 Feb 2026): Baseline model development

- Sprint 16–18 (10 Feb – 2 Mar 2026): CNN model development

- Sprint 19–20 (3 Mar – 16 Mar 2026): Evaluation outputs and repository updates

- Sprint 21–23 (17 Mar – 30 Mar 2026): Streamlit dashboard development

- Sprint 24–25 (31 Mar – 7 Apr 2026): UI refinement and testing

- Sprint 26–29 (8 Apr – 17 Apr 2026): Finalisation and submission

7. Scope:

In Scope:

- The following activities are included in the project scope:

- research into the problem area

- dataset identification and preparation

- preprocessing and environment setup

- development of baseline and CNN models

- model evaluation and comparison

- GitHub repository setup and maintenance

- README and supporting technical documentation

- Streamlit dashboard development

- dashboard-based testing and final validation

- final presentation and demo preparation

Out of Scope:

- The following activities are outside the project scope:

- commercial deployment

- mobile application development

- enterprise-scale hosting

- advanced production security implementation

- long-term maintenance after the academic submission

8. Budget:

This budget is offered as a practical estimate of a small project of AI prototype. It comprises of labour, infrastructure, development tools, equipments distribution, testing supports, and contingency.

Estimated Budget Breakdown:

Cost Area	                                                                    Estimated Cost

Labour cost	                                                                           £15,500

Cloud compute / model training	                               £1,800

Software / tools / licenses	                                              £1,000

Equipment / workstation allocation	                 £2,000

Storage / backup / repository services	                 £700

Testing / demo / deployment support	                 £800

Contingency reserve	                                                             £1,200

Total Estimated Budget:

£23,000

Budget Justification:

The budget of a small AI project of this nature should be around 23,000. The greatest cost area is labour since the project involves research, preprocessing, model development, evaluation, documentation, dashboard development and testing. A compute resource, development tools, workstations, storage, and final testing are other costs that will be needed. It also has a contingency reserve to cover any unexpected delay, rework on a model or integration problems.

9. Success Criteria:

- The project will be considered successful if:

- the dataset is selected and preprocessed correctly

- the baseline and CNN models are developed successfully

- both models are evaluated and performance metrics are generated

- the GitHub repository and README are complete and organised

- the Streamlit dashboard allows users to upload images and receive predictions

- the final system is tested successfully by the team

- all major deliverables are completed by 17 April 2026

- the team is able to present a working live demo on 20 April 2026

10. Risks:

Some key risks associated with the project are:

- delays in preprocessing or setup

- low model performance or poor prediction accuracy

- issues integrating the trained model into the Streamlit dashboard

- incomplete documentation close to submission

- time pressure during the final sprint phase

These risks can be reduced through regular sprint tracking, role clarity, testing, and early documentation updates.

8.	Stakeholders

- Team Members: Abdullah Hassan, Hamza Kounane, Altamash Khan, Mishal Zahra

- Supervisor: Dr.Kulvinder Panesar

- Client: Voung Mai

- Potential clients: Construction companies, Geologists, Sustainability programs.

11. Approval Statement

This project charter authorizes formally the SpaceLandMapper team to continue with the research, development, testing, documentation and final delivery of the AI prototype within the agreed scope, timeline and the estimated budget.