## Sprint Retrospective
SpaceLandMapper — Sprint Retrospective
Sprint | What Went Well | What Could Be Improved | Action Items for Next Sprint | Key Deliverable Completed | Velocity (Story Pts) | Team Morale
Sprint 1 Discovery & Planning 14 Oct 2025 – 10 Nov 2025 | • We confirmed the EuroSAT dataset early and aligned the team on the project direction. • We documented a clear class mapping so the pipeline could remain consistent later. • We started regular blog-style progress tracking to support agile evidence. | • The initial planning conversations took longer than expected before work became structured. • Role handovers were not yet formalised in the very first sprint. • Some planning tasks overlapped with early research and needed clearer boundaries. | • Keep a fixed weekly check-in rhythm. • Record key decisions in a shared document after each sprint. • Move the team into preprocessing and data setup with clearer ownership. | Dataset confirmation, label mapping and agile progress evidence | 7 | High
Sprint 2 Research & System Design 11 Nov 2025 – 1 Dec 2025 | • We defined preprocessing steps that could be reused across training and inference. • We created a reproducible split with a recorded seed and checked class balance. • The team’s technical direction became more concrete through data-focused work. | • Some dataset checks were discussed verbally instead of being documented immediately. • A few data-preparation activities depended heavily on one owner at first. • We needed tighter cross-checking of split assumptions before modelling began. | • Keep preprocessing notes version-controlled. • Cross-verify split ratios before model training starts. • Prepare baseline development tasks with clear evaluation ownership. | Preprocessing definition and reproducible train/validation/test split | 8 | High
Sprint 3 Research Report & Preparation 2 Dec 2025 – 5 Jan 2026 | • We clarified how the baseline benchmark would support fair comparison later. • We introduced experiment logging to improve reproducibility across runs. • The documentation quality improved while we prepared to move into implementation. | • This phase was still document-heavy, so technical progress felt slower than expected. • Some implementation tasks were postponed until the January build phase. • More explicit separation between reporting work and technical work was needed. | • Start the baseline build immediately in the next sprint. • Keep the experiment log updated for every major run. • Use the baseline outputs to guide the CNN development plan. | Baseline benchmark planning and experiment logging approach | 7 | Medium
Sprint 4 Setup & Data Preparation 6 Jan 2026 – 19 Jan 2026 | • We moved fully into the main build phase with a clearer technical focus. • The CNN and metric requirements were defined in a way that matched the test plan. • Evaluation outputs were planned early, which reduced confusion later. | • Some setup and model tasks still overlapped more than ideal. • A few dependencies needed checking before full model training began. • Progress logs could have been more detailed during technical setup. | • Keep model requirements tightly aligned with test cases. • Track all saved outputs and folders as they are created. • Move quickly from setup into full model execution. | CNN build planning and evaluation output requirements locked | 11 | High
Sprint 5 Baseline Development 20 Jan 2026 – 9 Feb 2026 | • We saved example predictions that later became useful for the dashboard and demo. • The dashboard direction became clearer once outputs were available to display. • The team linked evaluation evidence to user-facing presentation needs. | • Dashboard-related work still depended heavily on outputs being saved in the right format. • Some display decisions were made later than ideal. • More UI planning earlier would have reduced later rework. | • Use saved examples to support both dashboard tabs and presentation slides. • Make sure dashboard sections directly match the available outputs. • Prepare the model selector and dashboard logic in the next sprint. | Saved prediction examples and first working Streamlit dashboard base | 11 | High
Sprint 6 CNN Development 10 Feb 2026 – 2 Mar 2026 | • We improved the dashboard by making outputs easier to compare. • Error analysis helped us explain misclassifications more clearly. • The reproducibility guide made the project easier for others to run. | • Some explanation text in the dashboard needed several iterations to become concise. • A few model-to-dashboard links were tested late in the sprint. • We needed to keep wording more consistent across code, docs, and interface. | • Use the error analysis in the presentation to explain model behaviour. • Keep README instructions aligned with the actual environment setup. • Prepare the final packaging and submission structure next. | Model selector, error analysis and reproducible run guide | 9 | High
Sprint 7 Dashboard, Finalisation & Submission 3 Mar 2026 – 17 Apr 2026 | • We consolidated the repository, README, dashboard, and supporting documents. • The final prototype was presentation-ready with live prediction and saved evidence. • The submission pack became more consistent across technical and PM documents. | • Some final presentation assets were prepared close to the deadline. • Last-stage formatting and wording still needed careful checking. • A few deliverables would have benefited from earlier polishing. | • Complete one full rehearsal before presentation day. • Keep a backup copy of key screenshots and outputs. • Do a final submission check against the module requirements. | Final packaging, reproducibility check, and submission-ready repository | 5 | High